# HOGEYE 25 PERCENT GROWTH SCORECARD FEB MAY 2026

## Draft

# HogEye +25% Organic Traffic Scorecard (Feb-May 2026)

## Baseline Snapshot (locked 2026-02-10)

Baseline clicks (GSC top pages, last 28 days): 500

Baseline impressions (GSC top pages, last 28 days): 18,903

Baseline CTR: 2.65%

Baseline weighted avg position: 5.78

+25% click target line: 625 clicks

DataForSEO rank snapshot pulled for 25 tracked keywords (timeout at 100 keyword request; reduced and completed)

GA4 sessions and engaged sessions: blocked (current service account has no access to property 104905587)

## Scenario Forecast (directional model)

| Scenario | Projected Clicks | Lift vs Baseline | Gap to +25% Target |

|---|---:|---:|---:|

| Conservative | 506.67 | +1.33% | -118.33 |

| Base | 517.25 | +3.45% | -107.75 |

| Best | 557.58 | +11.52% | -67.42 |

Interpretation: current keyword/rank baseline does not yet model to +25% by May without additional execution lift (new coverage, stronger CTR gains, and/or more ranking keywords).

## Monthly Checkpoints Through May

| Month | Checkpoint Date | Base Path Clicks | +25% Target Line |

|---|---|---:|---:|

| 2026-02 | 2026-02-28 | 502.82 | 625.00 |

| 2026-03 | 2026-03-31 | 507.68 | 625.00 |

| 2026-04 | 2026-04-30 | 512.39 | 625.00 |

| 2026-05 | 2026-05-31 | 517.25 | 625.00 |

## Weekly Operating Rule (fail-fast)

Track three lines weekly in sheet tabs: baseline, base-path forecast, and actual.

Trigger adjustment if either condition occurs:

three consecutive weeks below base-path by >=10%, or

two consecutive monthly checkpoints below base-path by >=8%.

On trigger: re-prioritize next four posts/pages toward highest-impression non-brand queries and update titles/meta for CTR gains before publishing net-new pieces.

## Artifact Index

work/seo/benchmark/2026-02-10/Benchmark_Summary.csv

work/seo/benchmark/2026-02-10/Benchmark_Source_References.csv

work/seo/gsc_deep/2026-02-10_last_365d/

work/seo/plan/Forecast_25pct_assumptions.json

work/seo/plan/Forecast_25pct_keyword_model.csv

work/seo/plan/Forecast_25pct_scenarios.csv

work/seo/plan/Forecast_25pct_weekly_tracking.csv

work/seo/plan/Forecast_25pct_monthly_checkpoints.csv